BlueWhisper Phase 1 — Complete Requirements & Build Plan Functional Requirements · Non-Functional Requirements · Full Task Breakdown · Test Cases FR 22; NFR 18; Tasks 127; Test Cases 86. Total Estimated Build Time: 196 Hours ≈ 7 Weeks (Single Developer) April 2026 · Version 1.0 · Confidential

# 1. Phase 1 Overview

Phase 1 of BlueWhisper delivers the complete core product: one-to-one Bluetooth-only ephemeral chat with a 20-message session limit and a 10-second file vanish system. This document contains every functional and non-functional requirement, broken down into individual tasks of no more than 2 hours each, with a complete test plan covering all edge cases.

SCOPE BOUNDARIES ✅ Included in Phase 1: Profile setup, BT discovery, connection request, 1-to-1 chat, 20-msg limit, file sharing, 10s vanish, auto data wipe, background service, settings, Bangla/English. ❌ Excluded from Phase 1: Group chat, SOS alert, broadcast, premium subscription, B2B admin panel, mesh networking, WiFi Direct, any internet connectivity.

# 2. Functional Requirements (FR)

All 22 functional requirements for Phase 1. Each requirement is atomic, testable, and maps directly to one or more implementation tasks.

## FR-01 · User Profile

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-01.1 | App shall display onboarding screen on first launch only — never on subsequent launches | Critical | Install fresh → onboarding shown. Close + reopen → home screen shown directly. |
| FR-01.2 | User shall set a nickname of 1–15 characters. No email, phone, or password required. | Critical | Type 0 chars → Start disabled. Type 15 chars → accepted. Type 16th → blocked. |
| FR-01.3 | User shall select one avatar from 12 preset emoji options | Critical | All 12 avatars selectable. Selected avatar shows blue ring. Only one selectable at a time. |
| FR-01.4 | User shall select app language: English or Bangla | Critical | Select Bangla → entire UI switches to Bangla text. Select English → switches back. |
| FR-01.5 | Profile (nickname, avatar, language) shall be stored permanently in Android DataStore on device only | Critical | Profile persists after: app close, app kill, device restart. Never transmitted anywhere. |
| FR-01.6 | User shall be able to edit nickname and avatar from Settings at any time | High | Open settings → change nickname → save → home screen shows new name. |

## FR-02 · Bluetooth Discovery

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-02.1 | App shall automatically scan for nearby BlueWhisper devices when home screen is open | Critical | Open home screen → scanning starts within 3 seconds without any user action. |
| FR-02.2 | Nearby users shall appear on home screen within 5 seconds of both devices opening the app | Critical | Time from both apps open to card appearing: must be ≤ 5 seconds. |
| FR-02.3 | Each discovered user card shall show: nickname, avatar, estimated distance, signal strength colour | Critical | Card shows all 4 fields. Distance: Very close/Nearby/Far. Colour: green/amber/red. |
| FR-02.4 | Scanning shall use duty cycle: 20 seconds active, 8 seconds pause, repeat | High | Monitor BT state → scanning stops for ~8s every ~20s. Background drain ≤ 3%/hr. |
| FR-02.5 | Devices out of Bluetooth range shall be removed from the list within 10 seconds | Critical | Walk out of range → card disappears within 10 seconds. |
| FR-02.6 | User shall be able to toggle discoverability ON/OFF. When OFF, user is invisible to all nearby scans | High | Toggle OFF → other devices cannot see this user. Toggle ON → visible again within 3s. |
| FR-02.7 | Discovery shall stop immediately when a connection is established (battery saving) | Critical | After connection accepted → BT scanning stops. Verified by battery/log monitoring. |

## FR-03 · Connection Request

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-03.1 | Tapping Chat Now shall send a connection request to the selected user | Critical | Tap Chat Now → sender sees waiting screen. Request arrives on receiver within 2s. |
| FR-03.2 | Receiver shall see a full-screen accept/decline popup that cannot be missed | Critical | Receive request → full screen covers everything. Haptic vibration fires. Sound plays. |
| FR-03.3 | Receiver popup shall show: requester nickname, avatar, distance estimate | Critical | All 3 fields visible and accurate on receiver popup. |
| FR-03.4 | Receiver shall have 30 seconds to respond. Unanswered request auto-declines after 30s | Critical | No response for 30s → sender sees "No response". Both return to home. |
| FR-03.5 | Accepting a request shall open the chat screen on both devices simultaneously | Critical | Accept → both devices navigate to chat screen within 3 seconds. |
| FR-03.6 | Declining a request shall return both users to the home screen | Critical | Decline → sender sees "Not available". Both on home screen within 2s. |
| FR-03.7 | Only one active connection per device at any time | Critical | While in chat → Chat Now buttons on home screen are disabled for other users. |

## FR-04 · Real-Time Text Chat

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-04.1 | Text messages shall be delivered to the other device within 1 second over Bluetooth | Critical | Send message → appears on peer device within 1 second measured by stopwatch. |
| FR-04.2 | Messages shall be displayed in chat bubbles: sent messages right/blue, received messages left/grey | Critical | Sent = right-aligned blue gradient. Received = left-aligned grey. Verified visually. |
| FR-04.3 | Each message shall show a timestamp (time sent, not epoch) | High | Every bubble shows HH:MM format timestamp below the text. |
| FR-04.4 | A typing indicator shall appear when the other user is typing, updated every 2 seconds maximum | Medium | Type text → peer sees "X is typing..." within 2s. Stop typing → disappears within 3s. |
| FR-04.5 | Maximum message length shall be 200 characters per message | High | Type 200 chars → accepted. Type 201st → blocked. Counter shown near input. |
| FR-04.6 | All messages shall be stored in device RAM only (ViewModel). Nothing written to disk. | Critical | After disconnect → check Room DB and DataStore → zero messages found anywhere. |
| FR-04.7 | Both sent and received messages shall count toward the 20-message session limit | Critical | Send 10, receive 10 → counter shows 20/20. Both directions counted equally. |

## FR-05 · 20-Message Limit System

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-05.1 | A visible progress bar shall show messages used vs 20 maximum throughout the chat session | Critical | Progress bar visible below header at all times. Updates in real time. |
| FR-05.2 | Progress bar colour: green 0–13, yellow 14–16, orange 17–19, red at 20 | High | Send messages to each threshold → bar colour changes at exact counts 14, 17, 20. |
| FR-05.3 | Input field shall display remaining message count as placeholder text | High | Placeholder shows "(12 left)" updating to "(1 left)" as messages are sent/received. |
| FR-05.4 | Text input and send button shall be disabled when 20-message limit is reached | Critical | At 20 messages → input field greyed out, send button disabled. Cannot type. |
| FR-05.5 | An "End Chat" button shall appear when the 20-message limit is reached | Critical | At 20 messages → "End Chat & Clear All" button visible. Tapping wipes data and returns to home. |

## FR-06 · File Sharing

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-06.1 | User shall be able to send files from Camera, Gallery, or File manager via a bottom sheet picker | Critical | Tap attachment icon → sheet opens with 3 options. All 3 launch correct system pickers. |
| FR-06.2 | File size limit is 25MB. Files exceeding 25MB shall be rejected with an error message | Critical | Select 26MB file → error toast shown. Select 24.9MB file → transfer proceeds. |
| FR-06.3 | Supported file types: images (JPG PNG GIF WEBP), documents (PDF TXT), audio (MP3 AAC), video (MP4) | High | Test each type → transfers successfully. Unsupported type (e.g. .exe) → rejected. |
| FR-06.4 | File transfer progress shall be shown as a percentage bar on both sender and receiver screens | High | During transfer → both sides show progress bar with % updating in real time. |
| FR-06.5 | Only one file transfer is permitted at a time. Attachment button disabled during active transfer | High | Start transfer → attachment icon disabled. Complete → re-enabled. |
| FR-06.6 | Received file shall be stored in app cache directory as a temporary file only | Critical | Check device storage → file exists in cache only, not in permanent storage, until saved. |

## FR-07 · 10-Second File Vanish System

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-07.1 | Received file notification card shall appear in chat with a View button. No countdown starts until View is tapped. | Critical | Receive file → card shows. Wait 30s without tapping → countdown has NOT started. |
| FR-07.2 | Tapping View shall open a full-screen file viewer and start the 10-second countdown immediately | Critical | Tap View → full screen opens. Countdown starts from 10 at exactly that moment. |
| FR-07.3 | Countdown shall be accurate and visible: number in large text, coloured progress bar | Critical | Time countdown with stopwatch → zero reached in exactly 10 seconds ± 0.5s. |
| FR-07.4 | If user closes the viewer before 10 seconds, countdown shall continue running in background | Critical | Open viewer → close at 7s → reopen → shows remaining 3s (approximately). File then vanishes. |
| FR-07.5 | Tapping Save shall permanently save the file to Phone Storage/BlueWhisper/Received/ and stop the countdown | Critical | Tap Save → countdown stops immediately. File found in BlueWhisper folder. Survives disconnect. |
| FR-07.6 | When countdown reaches zero, the file shall be permanently deleted from device with a vanish animation | Critical | Let countdown reach 0 → viewer closes → vanish animation plays → file NOT found in storage anywhere. |
| FR-07.7 | Unsaved files shall be deleted on session disconnect regardless of countdown state | Critical | Receive file, do NOT save, then disconnect → file not found in any storage location. |
| FR-07.8 | File notification card in chat shall update to show "Saved ✓" or "Vanished 💨" after the outcome | Medium | After save → card shows "Saved ✓". After vanish → card shows "Vanished 💨". |

## FR-08 · Automatic Data Wipe on Disconnect

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-08.1 | ALL chat data shall be wiped within 2 seconds when either device manually disconnects | Critical | Disconnect → within 2s check ViewModel → messages list is empty. Remote profile is null. |
| FR-08.2 | Wipe shall trigger when: manual disconnect, app swiped away, Bluetooth turned off, devices go out of range | Critical | Test each trigger individually → wipe occurs in all 4 scenarios. |
| FR-08.3 | All unsaved temporary files in app cache shall be deleted on wipe | Critical | After wipe → check cache directory → zero temp files remain. |
| FR-08.4 | Session encryption key shall be zeroed in memory on wipe | Critical | After wipe → sessionKey in EncryptionEngine is null. ViewModel sessionKey is null. |
| FR-08.5 | A "Chat Cleared" animation screen shall play for 2 seconds after wipe, then navigate to home | High | After wipe → animated screen appears for 2s → auto-navigates to home screen. |
| FR-08.6 | User own profile, settings, and saved files shall NOT be wiped on disconnect | Critical | After disconnect → profile name, avatar, language, and saved files all intact. |

## FR-09 · Background Service & Notifications

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-09.1 | App shall run a foreground service to maintain BT scanning when app is in background | High | Minimize app → scanning continues. Another device can still find this device. |
| FR-09.2 | A persistent notification shall be shown while background service runs | Critical | Minimize app → notification shown: "BlueWhisper is scanning for nearby users." |
| FR-09.3 | A connection request received while app is in background shall trigger a notification | High | App minimized → receive request → notification appears with requester name. |
| FR-09.4 | Tapping the request notification shall open the app directly to the accept/decline screen | High | Tap notification → app opens to full-screen request popup. 30s timer active. |
| FR-09.5 | A file received while app is in background shall trigger a notification | High | App minimized → receive file → notification appears: "[name] sent you a file." |

## FR-10 · Settings Screen

| ID | Requirement | Priority | Testable Acceptance Criterion |
| --- | --- | --- | --- |
| FR-10.1 | Settings shall allow editing nickname (1–15 chars) and changing avatar | High | Change nickname → confirmed → chat and home screen immediately show new name. |
| FR-10.2 | Settings shall allow toggling discoverability (same effect as home screen toggle) | High | Toggle in settings → goes invisible → other devices cannot discover. |
| FR-10.3 | Settings shall allow switching language between English and Bangla | Critical | Switch language → entire app UI immediately switches language including all screens. |
| FR-10.4 | Settings shall show saved files count and total size, with option to open saved files screen | Medium | Shows "3 files · 8.4 MB". Tap → opens saved files list. |
| FR-10.5 | Settings shall allow clearing all saved files with a confirmation dialog | High | Tap Clear All → confirmation dialog appears → confirm → all saved files deleted → shows "0 files." |

# 3. Non-Functional Requirements (NFR)

Non-functional requirements define HOW WELL the system must work — performance, security, reliability, usability, compatibility, and battery efficiency. Every NFR has a measurable target and a verification method.

## NFR-01 · Performance

| ID | Requirement | Target Metric | Verification Method |
| --- | --- | --- | --- |
| NFR-01.1 | Message delivery latency over Bluetooth | ≤ 1 second end-to-end | Stopwatch test: send message, time until it appears on peer screen |
| NFR-01.2 | Device discovery time after both apps open | ≤ 5 seconds | Stopwatch: time from both screens open to first card appearing |
| NFR-01.3 | Session data wipe completion time after disconnect | ≤ 2 seconds | Check ViewModel state within 2s of disconnect trigger |
| NFR-01.4 | App launch to home screen time (returning user) | ≤ 2 seconds | Stopwatch from app icon tap to home screen fully rendered |
| NFR-01.5 | Connection establishment time after both users accept | ≤ 3 seconds | Time from Accept tap to chat screen appearing on both devices |
| NFR-01.6 | File transfer speed for a 5MB image | ≤ 30 seconds | Transfer 5MB file and time completion on receiver side |
| NFR-01.7 | UI frame rate during chat (no jank) | ≥ 60 FPS | Use Android Studio Frame Profiler during active chatting |
| NFR-01.8 | App memory usage during active chat session | ≤ 80 MB RAM | Android Studio Memory Profiler during 20-message session |

## NFR-02 · Battery Efficiency

| ID | Requirement | Target Metric | Verification Method |
| --- | --- | --- | --- |
| NFR-02.1 | Battery drain during background scanning (duty cycle mode) | ≤ 3% per hour | Leave app in background for 1 hour, measure battery % change |
| NFR-02.2 | Battery drain during a complete 20-message chat session | ≤ 5% total | Measure battery before session start and after session ends |
| NFR-02.3 | Battery drain when app is completely idle (no scanning) | ≤ 0.5% per hour | Kill active scanning, leave app open 1 hour, measure drain |
| NFR-02.4 | CPU wake lock held only during active file transfer (released after) | Max 5 seconds | Verify WakeLock released within 5s of transfer completion in logcat |

## NFR-03 · Security & Privacy

| ID | Requirement | Target Metric | Verification Method |
| --- | --- | --- | --- |
| NFR-03.1 | All messages encrypted in transit using AES-256-GCM | Zero plaintext bytes over BT | Capture BT packets with analyzer → verify all payloads are ciphertext |
| NFR-03.2 | Session key exchange using RSA-2048 before first message | Key exchange completes before any chat message is sent | Inspect logcat: KEY_EXCHANGE packet logged before first TEXT packet |
| NFR-03.3 | Session encryption key stored in RAM only, never written to disk | Key not found in any file after session | Check all storage after session → no key material found anywhere |
| NFR-03.4 | App shall never establish any network connection to any server or API | Zero bytes sent to any IP address | Network monitor (Charles Proxy or Android Network Inspector) shows zero traffic |
| NFR-03.5 | Zero message data written to disk at any point during or after session | No message files in any storage | Check Room DB, DataStore, cache, external storage → zero message records |
| NFR-03.6 | Temporary file (received, not saved) deleted within 2 seconds of disconnect | File absent from cache after wipe | Check cache directory within 2s of disconnect → file absent |

## NFR-04 · Compatibility

| ID | Requirement | Target Metric | Verification Method |
| --- | --- | --- | --- |
| NFR-04.1 | Minimum Android version supported | Android 8.0 (API 26) | Full functional test on Android 8.0 emulator and device |
| NFR-04.2 | Target Android version | Android 14 (API 34) | Full functional test on Android 14 device |
| NFR-04.3 | Minimum Bluetooth version required | Bluetooth 4.0 BLE | Test on device with BT 4.0 — all features must work |
| NFR-04.4 | Bluetooth 5.0+ devices must work with improved range | Works on all BT 5.0+ phones without modification | Test on Samsung A14 (BT 5.2), Xiaomi Redmi 12 (BT 5.3) |
| NFR-04.5 | App must work across different Android manufacturers (Samsung, Xiaomi, Walton, Symphony) | All features functional on all tested manufacturers | Test matrix of 5 device models — all pass full functional test |
| NFR-04.6 | Cross-device discovery: Samsung discovering Xiaomi and vice versa | Discovery works across different brands | Samsung phone discovers Xiaomi phone and vice versa ≤ 5s |

## NFR-05 · Reliability

| ID | Requirement | Target Metric | Verification Method |
| --- | --- | --- | --- |
| NFR-05.1 | App crash rate during normal usage | ≤ 0.5% of sessions | Run 200 complete sessions — maximum 1 crash allowed |
| NFR-05.2 | Bluetooth connection stability during 20-message session | Zero unexpected drops in normal indoor conditions | Complete 20 messages in 10 separate sessions — no unexpected disconnects |
| NFR-05.3 | File transfer completion rate for files under 25MB | ≥ 99% success rate | Transfer 100 files of varying types/sizes — 99 must complete |
| NFR-05.4 | Data wipe reliability — zero data left after ANY disconnect trigger | 100% of data wiped in 100% of disconnect scenarios | Test all 5 disconnect triggers × 20 repetitions each = 100 wipe tests — all must pass |
| NFR-05.5 | App must recover gracefully from Bluetooth being turned off mid-session | Clean disconnect, wipe triggers, returns to home | Turn BT off mid-chat → app returns cleanly to home, no crash, data wiped |

## NFR-06 · Usability & Accessibility

| ID | Requirement | Target Metric | Verification Method |
| --- | --- | --- | --- |
| NFR-06.1 | Onboarding completion time for a new user with no instructions | ≤ 30 seconds | Time 5 new users completing onboarding with zero instructions given |
| NFR-06.2 | Time to send first message after connection established | ≤ 10 seconds | From chat screen appearing to first message sent and received |
| NFR-06.3 | All touch targets minimum size | ≥ 48dp × 48dp | Use Android Layout Inspector to verify all interactive elements ≥ 48dp |
| NFR-06.4 | All text contrast ratios on backgrounds | ≥ 4.5:1 (WCAG AA) | Use accessibility checker → all text passes contrast check |
| NFR-06.5 | Complete app usable in Bangla language with no layout breaks | All screens display correctly in Bangla | Switch to Bangla → manually verify all 12 screens, no text overflow, no cut-off |
| NFR-06.6 | App size on device after installation | ≤ 20 MB | Check app size in Settings → App Info after release build |

# 4. Complete Task Breakdown — Max 2 Hours Per Task

Every task is atomic and completable in ≤ 2 hours. Tasks are ordered by build dependency — each group must be completed before the next. Categories: Setup, UI (interface), BT (Bluetooth), Logic (business logic), Test (testing).

HOW TO READ THIS TABLE • Task ID format: W1-T01 = Week 1, Task 01 ¦ Hours = estimated implementation time • Each task is self-contained and produces a specific, verifiable deliverable • Type: Setup=project config, UI=composable screen, BT=bluetooth code, Logic=ViewModel/UseCase, Test=test writing • Priority: Critical = blocks everything else ¦ High = needed for MVP ¦ Medium = important but not blocking

## Week 1 — Project Setup & Profile (16 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W1-T01 | Create Android project in Android Studio with Kotlin, set minSdk=26 targetSdk=34, add Gradle Kotlin DSL | Working project compiles and runs on emulator | 1.5h | Setup | Critical |
| W1-T02 | Add all Gradle dependencies: Compose BOM, Hilt, Room, DataStore, Nearby Connections API, Tink, Coil, Coroutines | All dependencies resolve with no version conflicts | 1.5h | Setup | Critical |
| W1-T03 | Create MVVM + Clean Architecture folder structure: presentation/, domain/, data/, bluetooth/, service/, di/ | Folder structure created, empty placeholder files in each module | 1h | Setup | Critical |
| W1-T04 | Set up Hilt dependency injection: AppModule, DatabaseModule, BluetoothModule with all @Provides methods | Hilt compiles, app builds with DI configured | 2h | Setup | Critical |
| W1-T05 | Set up Material 3 theme: colors.kt, typography.kt, shapes.kt with all 3 design system colour tokens | Theme applied to app, Composable previews render correctly | 1.5h | UI | High |
| W1-T06 | Add all permissions to AndroidManifest.xml: BT permissions (API 26–30 and API 31+), notifications, storage, foreground service | Manifest correct, no lint errors, permissions visible in app info | 1h | Setup | Critical |
| W1-T07 | Create UserProfile data class and UserProfileDataStore: save(), load(), update() with all 6 fields | Unit test: save profile → load → all 6 fields match exactly | 1.5h | Logic | Critical |
| W1-T08 | Build OnboardingScreen Composable: nickname input, 12 avatar grid, language selector, Start button | Screen renders correctly. All UI elements visible in Compose preview. | 2h | UI | Critical |
| W1-T09 | Implement OnboardingViewModel: nickname validation (1–15 chars), avatar selection state, language state, save action | Unit test: empty name → Start disabled. 15 char → enabled. 16th char blocked. | 1.5h | Logic | Critical |
| W1-T10 | Wire up onboarding flow: first launch → onboarding, subsequent launches → skip to home. Test both paths. | Install fresh → onboarding. Kill + reopen → home screen directly. | 1h | Logic | Critical |

## Week 2 — Bluetooth Discovery (18 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W2-T01 | Create NearbyConnectionsManager class with connectionsClient initialisation and SERVICE_ID constant | Class instantiates via Hilt without crash | 1h | BT | Critical |
| W2-T02 | Implement runtime permission request flow for BT (handles API 26–30 separately from API 31+) | Grant all perms → flow continues. Deny → friendly rationale shown. | 2h | Logic | Critical |
| W2-T03 | Implement startAdvertising() using Nearby Connections API Strategy.P2P_STAR with nickname as endpoint name | Device appears discoverable to nearby BT scanner. Verified with Nearby SDK demo app. | 2h | BT | Critical |
| W2-T04 | Implement startDiscovery() with EndpointDiscoveryCallback: onEndpointFound() adds device, onEndpointLost() removes | Found device → added to StateFlow list. Device turns off → removed within 10s. | 2h | BT | Critical |
| W2-T05 | Create NearbyDevice data class with: endpointId, nickname, avatarId, signalStrength, distanceEstimate, lastSeen | Data class serialises correctly. All fields accessible. | 0.5h | Logic | Critical |
| W2-T06 | Implement duty-cycle scanning: 20s active, 8s pause, repeat using Kotlin coroutine with delay | Monitor logcat: scan stops for ~8s every ~20s. Verified across 3 cycles. | 1.5h | BT | High |
| W2-T07 | Build HomeViewModel: manages nearbyDevices StateFlow, isScanning state, discoverability toggle | Unit test: startDiscovery → isScanning=true. Toggle off → isScanning=false. | 1.5h | Logic | Critical |
| W2-T08 | Build HomeScreen Composable: app bar with settings+visibility icons, scan status pill with animated dot | Screen renders. Dot animates. App bar icons visible and tappable. | 2h | UI | Critical |
| W2-T09 | Build UserCard Composable: avatar circle, nickname, distance text, signal dot, Chat Now button | Card renders correctly with all fields. Press state (scale 0.97) works. | 1.5h | UI | Critical |
| W2-T10 | Build empty state Composable for when no users are nearby: illustration, title, subtitle text | Empty state shown when nearbyDevices list is empty. Disappears when device found. | 0.5h | UI | High |
| W2-T11 | Integrate HomeViewModel with HomeScreen: observe nearbyDevices list, show cards or empty state | Real device discovered → card appears on screen within 5s. | 2h | Logic | Critical |
| W2-T12 | Implement discoverability toggle: when OFF, call stopAdvertising() and stopDiscovery(), update icon colour | Toggle OFF → other device list clears within 10s. Toggle ON → device reappears. | 1h | BT | High |

## Week 3 — Connection Request Flow (16 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W3-T01 | Implement requestConnection() in NearbyConnectionsManager with ConnectionLifecycleCallback skeleton | Call requestConnection → callback fires. No crash. Logged in logcat. | 1.5h | BT | Critical |
| W3-T02 | Implement sender waiting state: ConnectionRequestSenderScreen with avatar, name, animated dots, 30s countdown arc | Screen renders with countdown. Timer counts down accurately. | 2h | UI | Critical |
| W3-T03 | Build ConnectionViewModel: manages request state (IDLE, PENDING, ACCEPTED, REJECTED, TIMEOUT) as StateFlow | Unit test: state transitions IDLE→PENDING→ACCEPTED all correct. | 1.5h | Logic | Critical |
| W3-T04 | Implement ConnectionLifecycleCallback.onConnectionInitiated(): show receiver popup, store endpointId | Receiver popup triggers when request arrives. endpointId stored correctly. | 1.5h | BT | Critical |
| W3-T05 | Build ConnectionRequestReceiverScreen: full-screen popup with avatar, name, distance, Accept button, Not Now button, countdown bar | Screen is full-screen. Both buttons visible. Bar drains over 30s. | 2h | UI | Critical |
| W3-T06 | Implement acceptConnection() and rejectConnection() in callback, update ViewModel state accordingly | Accept → onConnectionResult fires STATUS_OK. Reject → STATUS_REJECTED fires. | 1h | BT | Critical |
| W3-T07 | Implement 30-second timeout: coroutine started in ViewModel, cancels on response, auto-declines on expiry | No response → rejectConnection() called at exactly 30s. Both sides return home. | 1.5h | Logic | Critical |
| W3-T08 | Implement onConnectionResult callback: STATUS_OK → navigate to chat, ERROR → show error, REJECTED → show message | All 3 result cases handled. Correct navigation occurs for each. | 1.5h | BT | Critical |
| W3-T09 | Stop scanning + advertising immediately on successful connection in onConnectionResult STATUS_OK | After connection → logcat shows stopDiscovery() and stopAdvertising() called. | 0.5h | BT | Critical |
| W3-T10 | Add haptic feedback (2 short vibrations) and sound on connection established | On accept → phone vibrates twice. Sound plays (respects silent mode). | 0.5h | Logic | Medium |
| W3-T11 | Implement onDisconnected callback: trigger data wipe, navigate to disconnect animation screen | Forcibly disconnect → onDisconnected fires → wipe executes → correct screen shows. | 1.5h | BT | Critical |
| W3-T12 | Add Bluetooth state BroadcastReceiver: detect BT turned off mid-session → trigger wipe | Turn off BT during active connection → wipe triggers within 2s. | 1h | BT | Critical |

## Week 4 — Chat Screen & Message System (18 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W4-T01 | Create Message data class with: index(Int), content(String), timestamp(Long), direction(SENT/RECEIVED), type(TEXT/FILE_NOTIFICATION) | Data class created. Unit test: all fields readable after construction. | 0.5h | Logic | Critical |
| W4-T02 | Create MessagePacket data class (wire format): i(Byte), c(String), t(Int), tp(MessageType). Add Gson serialisation. | Unit test: serialise packet → deserialise → all fields identical to original. | 1h | Logic | Critical |
| W4-T03 | Implement MessageSerializer: toByteArray() and fromByteArray() with UTF-8 encoding and Bangla support | Unit test: English + Bangla text round-trip with zero data loss. | 1h | Logic | Critical |
| W4-T04 | Implement DEFLATE compression: compress(ByteArray) and decompress(ByteArray) using java.util.zip | Unit test: compress "Hello" → decompress → "Hello". Bangla text same. | 1h | Logic | High |
| W4-T05 | Implement EncryptionEngine: generateKeyPair(), encryptSessionKey(), decryptSessionKey(), encrypt(data,key), decrypt(data,key) | Unit test: encrypt text → decrypt → identical original. Wrong key → exception. | 2h | Logic | Critical |
| W4-T06 | Implement key exchange flow: on connection → send public key → receive peer public key → derive session key → store in RAM | Integration test: two devices connect → both have same session key → verified by successful decrypt. | 2h | BT | Critical |
| W4-T07 | Implement sendMessage() in NearbyConnectionsManager: serialize → compress → encrypt → Payload.fromBytes() → sendPayload() | Send "Hello" → verify encrypted bytes arrive on peer → decrypt to "Hello". | 1.5h | BT | Critical |
| W4-T08 | Implement PayloadCallback.onPayloadReceived() for BYTES type: decrypt → decompress → deserialize → dispatch to ViewModel | Receive payload → correct Message appears in ChatViewModel._messages list. | 1.5h | BT | Critical |
| W4-T09 | Build ChatViewModel: _messages MutableList, messageCount StateFlow, isLimitReached, sendMessage(), onMessageReceived() | Unit test: add 20 messages → isLimitReached=true. 21st message rejected. | 1.5h | Logic | Critical |
| W4-T10 | Build ChatScreen Composable skeleton: header with avatar/name/status/disconnect, progress bar area, message list, input area | Screen renders with all areas. No data yet — static layout visible. | 2h | UI | Critical |
| W4-T11 | Build MessageBubble Composable: SENT (right, gradient) and RECEIVED (left, grey) variants with timestamp | Both bubble types render. Correct alignment. Timestamp visible. | 1.5h | UI | Critical |
| W4-T12 | Build MessageProgressBar Composable: animates width, colour transitions at 14/17/20 messages | Colour transitions at correct message counts. Animation smooth. | 1h | UI | High |
| W4-T13 | Build ChatInputArea Composable: text field, emoji button, attach button, send button (active/disabled states) | Input renders. Send active with text, disabled when empty. 200-char limit enforced. | 1.5h | UI | Critical |
| W4-T14 | Implement typing indicator: debounced 2s, send TYPING packet, receiver shows "X is typing...", disappears 3s after last keystroke | Type → peer sees indicator within 2s. Stop → disappears within 3s. | 1h | Logic | Medium |
| W4-T15 | Wire up ChatScreen to ChatViewModel: observe messages, render list, send on button tap, limit reached banner | Full chat flow works end-to-end: type → send → appears on both screens. | 2h | UI | Critical |

## Week 5 — File Transfer System (16 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W5-T01 | Build FilePickerBottomSheet Composable: drag handle, title, 4 option tiles (Camera, Gallery, Document, Audio), Cancel button | Sheet renders. Slides up smoothly. All 4 tiles visible. Drag-to-dismiss works. | 1.5h | UI | Critical |
| W5-T02 | Implement Camera intent launcher: request CAMERA permission if not granted, launch camera, receive image result | Grant camera → camera opens → take photo → URI returned to ViewModel. | 1.5h | Logic | Critical |
| W5-T03 | Implement Gallery picker using ActivityResultContracts.GetContent for image types | Launch picker → select image → URI returned. Multiple image types work. | 1h | Logic | Critical |
| W5-T04 | Implement File picker using ActivityResultContracts.OpenDocument for all supported types | Launch picker → select PDF/MP3/MP4/TXT → URI returned correctly. | 1h | Logic | High |
| W5-T05 | Implement file size validation: get file size from URI, reject if > 25MB with toast message | Select 26MB file → toast shown "File too large. Max 25MB". Transfer not started. | 1h | Logic | Critical |
| W5-T06 | Implement sendFile() in NearbyConnectionsManager: send FILE_META packet first, then Payload.fromFile(pfd) | File transfer starts. Progress callback fires. FILE_META packet arrives before file. | 2h | BT | Critical |
| W5-T07 | Implement PayloadCallback.onPayloadReceived() for FILE type: create ReceivedFile, store in ViewModel, show notification card in chat | File payload received → ReceivedFile object created → card appears in chat. | 1.5h | BT | Critical |
| W5-T08 | Implement PayloadTransferUpdate handling: update progress % on both sides, handle SUCCESS and FAILURE states | Progress bar updates in real-time on both screens. 100% triggers correct next state. | 1.5h | BT | Critical |
| W5-T09 | Build FileTransferProgressCard Composable: show filename, size, animated progress bar with %, status text | Card renders during transfer. Progress updates every ~500ms. Completion shown. | 1.5h | UI | High |
| W5-T10 | Build ReceivedFileCard Composable: filename, size, View button (pre-open), "Saved ✓" state, "Vanished 💨" state | All 3 states render correctly. View button only visible in pre-open state. | 1h | UI | Critical |
| W5-T11 | Create FileTransferManager: manages temp file path, progress state, cleans up temp files on request | Unit test: cleanup() → temp file deleted. Verify via File.exists() = false. | 1h | Logic | Critical |
| W5-T12 | Implement file metadata packet serialisation: FileMetadata data class, serialise payloadId+fileName+fileSize+fileType | Unit test: serialise FileMetadata → deserialise → all fields identical. | 0.5h | Logic | High |

## Week 6 — 10-Second Vanish System (14 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W6-T01 | Create ReceivedFile state machine: TRANSFERRING → RECEIVED_UNVIEWED → VIEWING → SAVED/VANISHED with enum class | Unit test: all valid state transitions work. Invalid transitions throw exception. | 1h | Logic | Critical |
| W6-T02 | Build FileViewerViewModel: remainingSeconds StateFlow, startCountdown(), stopCountdown(), saveFile(), vanishFile() | Unit test: startCountdown → remainingSeconds counts 10→0 in exactly 10 seconds. | 1.5h | Logic | Critical |
| W6-T03 | Implement countdown coroutine: delay(1000) loop in viewModelScope, fires vanishFile() at 0, survives screen close | Viewer closed → countdown continues in ViewModel → reaches 0 → vanishFile() fires. | 2h | Logic | Critical |
| W6-T04 | Implement vanishFile(): file.delete() with verification, retry with zero-overwrite if delete fails, post VANISHED event | Unit test: create temp file → vanishFile() → File.exists() returns false. | 1h | Logic | Critical |
| W6-T05 | Build FileViewerScreen Composable: full-screen layout, close button, file preview area, countdown card, save button | Screen renders full-screen. All elements visible. Close button works. | 2h | UI | Critical |
| W6-T06 | Implement file preview rendering: images with Coil (pinch-to-zoom), PDF first page render, audio waveform placeholder, video thumbnail | All 4 file types render a meaningful preview. No crash on any type. | 2h | UI | High |
| W6-T07 | Build CountdownCard Composable: large number (48sp), colour-changing progress bar (purple→orange→red at 3s), glow shadow | Colours change at correct thresholds. Bar accurate. Number clear and large. | 1.5h | UI | Critical |
| W6-T08 | Implement saveFile() action: copy from cache to Phone Storage/BlueWhisper/Received/, create Room SavedFile record, stop countdown | Save → file exists in permanent folder → Room record created → countdown stopped. | 1.5h | Logic | Critical |
| W6-T09 | Build vanish animation: screen flash, particle/fade animation using Compose AnimatedVisibility and keyframes | Animation plays on vanish. 1200ms duration. Viewer closes after animation. | 1h | UI | High |
| W6-T10 | Wire FileViewerScreen to FileViewerViewModel: View tap → state=VIEWING → countdown starts → auto-close on vanish | Full flow: tap View → countdown runs → reaches 0 → viewer closes → card shows "Vanished 💨". | 1.5h | Logic | Critical |

## Week 7 — Data Wipe, Disconnect & Background Service (16 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W7-T01 | Implement DisconnectUseCase: clear _messages list, null remoteUser, null sessionKey via Arrays.fill(), delete temp files | Unit test: execute() → messages.isEmpty()==true, sessionKey==null, temp files absent. | 1.5h | Logic | Critical |
| W7-T02 | Build DisconnectAnimationScreen Composable: Wind icon, "Chat Cleared" text, privacy message, teal info card, auto-navigate after 2s | Screen renders. Auto-navigates to home after exactly 2 seconds. | 1.5h | UI | High |
| W7-T03 | Implement Lottie particle animation for disconnect screen (or frame-by-frame compose animation if Lottie not used) | Animated particles visible on disconnect screen for 2 second duration. | 2h | UI | Medium |
| W7-T04 | Create BluetoothForegroundService: starts on app launch, maintains BT connection in background, shows persistent notification | Service running → minimize app → notification visible → BT still active. | 2h | Logic | Critical |
| W7-T05 | Implement foreground service notification channel, notification builder, startForeground() call with correct type | Notification channel created. Notification shows correct text and icon. | 1h | Logic | Critical |
| W7-T06 | Implement connection request notification when app is backgrounded: build notification with requester name, tap action | Background → receive request → notification appears with name. Tap → opens popup. | 2h | Logic | High |
| W7-T07 | Implement file received notification when app is backgrounded: notification with sender name, tap action | Background → receive file → notification appears. Tap → opens chat with file card. | 1.5h | Logic | High |
| W7-T08 | Build No-Bluetooth error screen: variants for BT off, permission denied, BLE unsupported. Auto-recover on BT on. | Each variant shows correct message. BT off → turn on → app continues automatically. | 2h | UI | Critical |
| W7-T09 | Implement BroadcastReceiver for ACTION_STATE_CHANGED: detect BT turned off → trigger disconnect + wipe | Turn BT off mid-chat → wipe triggers within 2s. App returns to home. | 1.5h | BT | Critical |
| W7-T10 | Implement NavGraph using Jetpack Navigation Compose: all routes defined, back stack managed correctly | Navigate all 12 screen paths → no back stack issues. Back button works on each screen. | 1.5h | UI | High |

## Week 8 — Settings, Saved Files & Polish (14 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W8-T01 | Build SettingsScreen Composable: profile section, visibility toggle, language selector, storage section, about section | Settings screen renders all 5 sections. Toggle and chevron rows visible. | 2h | UI | High |
| W8-T02 | Implement profile edit flow in settings: edit nickname inline, change avatar via grid dialog, save updates DataStore | Change nickname in settings → home screen shows new name immediately. | 1.5h | Logic | High |
| W8-T03 | Implement language switch in settings: switch EN→BN or BN→EN, restart activity, all 12 screens update | Switch to Bangla → all screens render in Bangla. No layout overflow. | 1.5h | Logic | Critical |
| W8-T04 | Set up strings.xml with all UI strings for English. Create strings.xml (bn) with all Bangla translations. | All hardcoded strings moved to resources. Bangla file has all keys. | 2h | Logic | Critical |
| W8-T05 | Build SavedFilesScreen Composable: date section headers, file cards with thumbnail/icon, 3-dot options menu, Clear All button | Screen renders all saved files grouped by date. Options menu opens correctly. | 2h | UI | Medium |
| W8-T06 | Implement SavedFileDao in Room: insertFile(), getAllFiles() Flow, softDeleteFile(), hardDeleteAllFiles(), getTotalSize() | Unit test all 5 DAO methods against in-memory Room database. | 1.5h | Logic | High |
| W8-T07 | Implement Clear All Saved Files: confirmation dialog → delete all files from filesystem → hardDeleteAllFiles() Room | Confirm clear → all files gone from folder → Room count = 0. | 1h | Logic | High |
| W8-T08 | Implement file options menu (3-dot): Open in system viewer, Share via system share sheet, Delete with confirmation | All 3 options work. Delete removes from folder and Room. Share opens share sheet. | 2h | Logic | Medium |

## Week 9 — Full Testing, Bug Fixes & Play Store Prep (20 hours)

| Task ID | Task Description | Deliverable / Done When | Hours | Type | Priority |
| --- | --- | --- | --- | --- | --- |
| W9-T01 | Write and run unit tests for all 7 Use Cases: SendMessage, ReceiveFile, Disconnect, SaveFile, VanishFile, EncryptMessage, ValidateProfile | All 7 use case unit test suites pass. 100% of critical paths covered. | 2h | Test | Critical |
| W9-T02 | Write and run unit tests for all 5 ViewModel classes: ChatViewModel, HomeViewModel, FileViewerViewModel, ConnectionViewModel, SettingsViewModel | All ViewModel unit tests pass. State transitions verified. | 2h | Test | Critical |
| W9-T03 | Write and run unit tests for MessageSerializer: round-trip with English, Bangla, emoji, special chars, max length, empty string | All serialiser tests pass. Zero data loss on any character type. | 1h | Test | Critical |
| W9-T04 | Write and run unit tests for EncryptionEngine: encrypt/decrypt round-trip, wrong key rejection, key zeroing, nonce uniqueness | All encryption tests pass including security boundary tests. | 1.5h | Test | Critical |
| W9-T05 | Write and run unit tests for FileVanishTimer: 10s accuracy, save stops countdown, background continuation, disconnect wipe | All timer tests pass. Timing accurate within 0.5 seconds. | 1.5h | Test | Critical |
| W9-T06 | Write Espresso UI tests for onboarding flow: empty name blocks start, avatar selection, language switch, start navigates home | All 4 onboarding UI tests pass on emulator. | 1.5h | Test | High |
| W9-T07 | Two-device integration test: discovery, connection, send 20 messages, verify all received, verify both counters match | 20-message session completes successfully on 2 real devices. | 2h | Test | Critical |
| W9-T08 | Two-device file transfer test: send each file type (JPG, PDF, MP3, MP4), verify receipt, test 10s vanish accuracy | All 4 file types transfer and vanish correctly on real devices. | 2h | Test | Critical |
| W9-T09 | Data wipe test battery: test all 5 disconnect triggers × 4 times each = 20 wipe tests. Verify zero data after each. | All 20 wipe tests pass. Zero messages/files found after any trigger. | 2h | Test | Critical |
| W9-T10 | Edge case test: devices at range limit (~25–30m), low battery device, phone call interruption, app kill during transfer | All edge cases handled gracefully. App returns to clean state. | 2h | Test | High |
| W9-T11 | Performance test: measure message latency (×20), app startup (×10), wipe time (×20), memory during session | All metrics within NFR targets. Results documented. | 1h | Test | High |
| W9-T12 | Cross-device compatibility test on 5 device models: Samsung A14, Xiaomi Redmi 12, Walton Primo, Samsung J7 (API 26), Realme C55 | All 5 devices complete full flow test without crash or functional failure. | 2h | Test | Critical |
| W9-T13 | Security verification: monitor network traffic during session, check storage after session, verify no plaintext BT packets | Zero network traffic. Zero messages in storage. Zero plaintext in BT packets. | 1h | Test | Critical |
| W9-T14 | Build signed release APK: configure ProGuard, test release build on 2 devices, verify no regression | Release APK installs and passes full smoke test on 2 devices. | 1h | Test | Critical |

# 5. Total Time Summary

| Week | Focus Area | Tasks | Total Hours | Cumulative |
| --- | --- | --- | --- | --- |
| Week 1 | Project Setup & User Profile | 10 tasks | 16h | 16h |
| Week 2 | Bluetooth Discovery | 12 tasks | 18h | 34h |
| Week 3 | Connection Request Flow | 12 tasks | 16h | 50h |
| Week 4 | Chat Screen & Message System | 15 tasks | 18h | 68h |
| Week 5 | File Transfer System | 12 tasks | 16h | 84h |
| Week 6 | 10-Second Vanish System | 10 tasks | 14h | 98h |
| Week 7 | Data Wipe, Disconnect & Background | 10 tasks | 16h | 114h |
| Week 8 | Settings, Saved Files & Polish | 8 tasks | 14h | 128h |
| Week 9 | Full Testing, Bug Fix & Release | 14 tasks | 20h | 148h |

TOTAL ESTIMATED TIME 127 development tasks + 14 testing tasks = 141 total tasks Total Hours: 148 hours of actual work At 6 hours/day (realistic developer pace): 148 ÷ 6 = ~25 working days = 5 calendar weeks At 4 hours/day (part-time): 148 ÷ 4 = ~37 days = 7.5 calendar weeks Buffer for unexpected issues (+20%): 148 × 1.2 = ~178 hours total with buffer Recommended Timeline: 8 weeks from start to Play Store submission

# 6. Complete Edge Cases to Test

Every edge case that could cause incorrect behavior, crash, or security failure. These must ALL pass before Play Store submission.

## 6.1 Bluetooth & Connectivity Edge Cases

| EC-ID | Edge Case Scenario | Expected Behavior | Risk Level |
| --- | --- | --- | --- |
| EC-BT-01 | BT turned off while app is on home screen scanning | Scanning stops gracefully. Error screen shown. BT turned on → scanning resumes. | D97706 |
| EC-BT-02 | BT turned off exactly while connection request is in-flight (30s window) | Request fails cleanly. Both devices return to home. No crash. | DC2626 |
| EC-BT-03 | BT turned off at exactly the moment a message is being sent | Message fails. Disconnect wipe triggers. App returns to home. | DC2626 |
| EC-BT-04 | BT turned off during file transfer (at 50% progress) | Transfer cancelled. Temp file deleted. Wipe triggers. Home screen shown. | DC2626 |
| EC-BT-05 | Phone call received during active chat session | Android may disconnect BT. Wipe triggers. Call handled normally. App returns to home. | DC2626 |
| EC-BT-06 | Devices at exact range boundary (~28–32m, intermittent signal) | Connection may be unstable. If dropped → clean wipe. No frozen state. | D97706 |
| EC-BT-07 | Three devices all with app open. Device A connects to B. What does C see? | C still sees both A and B as available. When A+B are connected, C cannot connect to them. | D97706 |
| EC-BT-08 | Same device tries to connect to itself (developer testing scenario) | Self-connection prevented. No crash. Error logged. | D97706 |
| EC-BT-09 | Two users simultaneously tap Chat Now on each other at same moment | One connection request wins. Other gets "busy" state. No double-connection. | DC2626 |
| EC-BT-10 | BT adapter reset by Android OS (background power management) | App detects reset via BroadcastReceiver. Restarts scanning gracefully. | D97706 |

## 6.2 Message & Chat Edge Cases

| EC-ID | Edge Case Scenario | Expected Behavior | Risk Level |
| --- | --- | --- | --- |
| EC-MSG-01 | User sends 20th message at exact same time as receiving 20th message (race condition) | Counter safely reaches 20. Input disabled. No 21st message accepted from either side. | DC2626 |
| EC-MSG-02 | Message contains 200 characters of Bangla text (multi-byte UTF-8) | Bangla 200-char message serialises, compresses, encrypts, transmits, and decodes correctly. | DC2626 |
| EC-MSG-03 | Message contains emoji (4-byte Unicode, e.g. 🔥 🎉 💨) | Emoji preserved through full encode/decode cycle. Renders correctly in bubble. | D97706 |
| EC-MSG-04 | Message content is exactly 200 characters (boundary test) | 200-char message accepted and sent. 201-char input blocked at input level. | D97706 |
| EC-MSG-05 | Empty message (only spaces or whitespace typed) | Send button disabled for whitespace-only input. Blank message never sent. | D97706 |
| EC-MSG-06 | Messages arrive out of order due to BT packet reordering | Messages displayed in order of receipt timestamp. No crash on ordering. | D97706 |
| EC-MSG-07 | Typing indicator arrives but session is at 20/20 (no more messages possible) | Typing indicator still shows (they may be unaware of limit). No crash. | undefined |
| EC-MSG-08 | ViewModel is cleared by Android OS (low memory) during active chat | OS should not kill foreground service. If it does → clean wipe on resume. | D97706 |

## 6.3 File Transfer Edge Cases

| EC-ID | Edge Case Scenario | Expected Behavior | Risk Level |
| --- | --- | --- | --- |
| EC-FILE-01 | User selects a file that is deleted between selection and send | ContentResolver.openFileDescriptor() throws exception → error toast shown. | DC2626 |
| EC-FILE-02 | File is exactly 25MB (boundary condition) | 25.0MB file accepted and transfer begins. 25.1MB rejected. | D97706 |
| EC-FILE-03 | Transfer starts then sender walks out of range at 60% progress | Transfer fails with FAILURE status. Temp file on receiver deleted. Error shown. | DC2626 |
| EC-FILE-04 | Receiver device runs out of storage during file save | IOException caught → error toast "Not enough storage". Temp file not corrupted. | DC2626 |
| EC-FILE-05 | User taps View, countdown starts, then app crashes and restarts | On restart → session is gone (wipe). File in cache is deleted by cleanup routine. | DC2626 |
| EC-FILE-06 | User taps Save at exactly the same moment countdown reaches 0 (race condition) | Atomic state check: SAVED takes priority over VANISHED. File is saved. | DC2626 |
| EC-FILE-07 | File viewer opened for video but no video codec available on device | Fallback to thumbnail + play icon. No crash. | D97706 |
| EC-FILE-08 | Camera file is very large (4K photo ~15MB). Transfer starts immediately. | Transfer works (< 25MB). Progress bar shown. Completes successfully. | D97706 |
| EC-FILE-09 | User rapidly taps View button multiple times | Countdown starts only once. Multiple taps have no additional effect. | D97706 |
| EC-FILE-10 | Countdown running, user puts phone in pocket (screen off) | Countdown coroutine continues in ViewModel. Screen off does not pause it. | DC2626 |

## 6.4 Data Wipe Edge Cases

| EC-ID | Edge Case Scenario | Expected Behavior | Risk Level |
| --- | --- | --- | --- |
| EC-WIPE-01 | App is force-stopped by user during active chat via recent apps | onDestroy() or service stop → wipe triggers. On reopen → clean home screen. | DC2626 |
| EC-WIPE-02 | Device battery dies at 0% during active chat | OS kills app. On restart → ViewModel is empty (new instance). No stale data. | DC2626 |
| EC-WIPE-03 | Device restarts (reboot) during active chat | New process on restart. All RAM cleared by OS. App opens clean. | D97706 |
| EC-WIPE-04 | Wipe is called twice in rapid succession (double-trigger from two events simultaneously) | Wipe is idempotent. Second call on already-empty state causes no crash. | D97706 |
| EC-WIPE-05 | File save and wipe trigger at same instant (race condition) | If file save completed before wipe → file preserved. If not → file deleted with wipe. | DC2626 |
| EC-WIPE-06 | Profile data (nickname, avatar) survives wipe correctly | After wipe → profile unchanged. Settings unchanged. Saved files unchanged. | DC2626 |
| EC-WIPE-07 | Wipe triggered while disconnect animation is already playing | No crash. Animation completes normally or is interrupted gracefully. | D97706 |

## 6.5 Security Edge Cases

| EC-ID | Edge Case Scenario | Expected Behavior | Risk Level |
| --- | --- | --- | --- |
| EC-SEC-01 | Attacker builds modified app that skips key exchange and sends plaintext | Receiver rejects messages that fail decryption. Session never becomes usable. | DC2626 |
| EC-SEC-02 | Attacker attempts to replay an old captured BT packet | GCM authentication tag fails. Message discarded silently. | DC2626 |
| EC-SEC-03 | Heap dump taken while session is active (developer mode) | Session key is in RAM. This is acceptable and documented. Key is zeroed on wipe. | D97706 |
| EC-SEC-04 | Device storage scanned after disconnect for any message data | Zero message records in Room, DataStore, cache, or external storage. | DC2626 |
| EC-SEC-05 | Network traffic monitor running during entire session | Zero bytes sent to any IP address at any time during session. | DC2626 |

# 7. Complete Test Cases (86 Total)

Every test case maps to a functional or non-functional requirement. Pass/fail is binary. Edge cases are included in the test steps where relevant.

## 7.1 Profile & Onboarding Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-P01 | FR-01.1 | First launch shows onboarding | 1. Fresh install 2. Open app | Onboarding screen shown. Profile setup required. | Verify does NOT show on 2nd launch |
| TC-P02 | FR-01.2 | Nickname empty → Start disabled | 1. Open onboarding 2. Leave name empty 3. Check Start button | Start button is greyed out and untappable | Try whitespace-only → still disabled |
| TC-P03 | FR-01.2 | Nickname 15 chars → accepted | 1. Type exactly 15 chars 2. Tap Start | Profile saved. Navigates to home. | 16th character cannot be typed |
| TC-P04 | FR-01.3 | Avatar selection works | 1. Tap avatar 3 2. Tap avatar 7 3. Tap Start | Avatar 7 is selected (ring shown). Profile saves avatarId=7. | Only one selected at a time |
| TC-P05 | FR-01.4 | Language switch EN→BN | 1. Select Bangla on onboarding 2. Tap Start | All home screen text in Bangla script | Verify Noto Sans Bengali renders correctly |
| TC-P06 | FR-01.5 | Profile persists after device restart | 1. Set profile 2. Restart device 3. Open app | Same nickname, avatar, language shown | Verify DataStore not cleared |
| TC-P07 | FR-01.6 | Settings: edit nickname | 1. Open settings 2. Change name to "TestUser" 3. Save 4. Go to home | Home screen shows "TestUser" in scan status | Original name lost — confirm dialog? |

## 7.2 Bluetooth Discovery Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-D01 | FR-02.1 | Scanning starts automatically | 1. Open home screen 2. Wait 3s | Scanning status pill visible. Animated dot pulsing. | Without any user interaction |
| TC-D02 | FR-02.2 | Nearby device appears within 5s | 1. Open app on Device A 2. Open app on Device B 3. Stopwatch | Device B card appears on A within 5 seconds. | Test multiple times — must ALWAYS be ≤5s |
| TC-D03 | FR-02.3 | Card shows all 4 fields | 1. See device card on home screen | Card shows: emoji avatar, nickname text, distance label, coloured dot | Distance label: Very close / Nearby / Far |
| TC-D04 | FR-02.5 | Out-of-range device removed | 1. Walk device B out of range 2. Wait | Card for B disappears within 10 seconds. | Test at 30m+ distance |
| TC-D05 | FR-02.6 | Invisible mode hides device | 1. Toggle visibility OFF on Device A 2. Check Device B home screen | Device A NOT visible on Device B. Invisible icon on A. | "Invisible" device can still see others |
| TC-D06 | FR-02.7 | Scanning stops after connection | 1. Establish connection 2. Check logcat | stopDiscovery() and stopAdvertising() both called immediately after connection. | Battery saving critical |

## 7.3 Connection Request Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-C01 | FR-03.1 | Chat Now sends request | 1. Tap Chat Now on card 2. Check peer screen | Peer receives full-screen popup within 2 seconds. | Sender sees waiting screen |
| TC-C02 | FR-03.2 | Receiver popup is full-screen | 1. Receive connection request | Full screen popup covers entire screen. Cannot be dismissed by back button. | Haptic vibration fires |
| TC-C03 | FR-03.3 | Popup shows correct info | 1. Device A sends request to B 2. Check B popup | B popup shows A nickname, A avatar, and distance estimate. | Distance must be accurate |
| TC-C04 | FR-03.4 | 30s timeout auto-declines | 1. Send request 2. Do not respond 3. Wait 30s | Sender: "No response". Both on home screen. | Time with stopwatch — must be 30s ± 2s |
| TC-C05 | FR-03.5 | Accept opens chat on both | 1. Send request 2. Accept | Both devices show chat screen within 3 seconds. | Chat screen shows connected indicator |
| TC-C06 | FR-03.6 | Decline returns both to home | 1. Send request 2. Tap Not Now | Sender sees "Not available". Both on home screen. | No data remains from declined request |
| TC-C07 | EC-BT-09 | Simultaneous mutual request | 1. Both tap Chat Now simultaneously | One connection forms. No double-session. No crash. | Must resolve within 5 seconds |

## 7.4 Chat & 20-Message Limit Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-M01 | FR-04.1 | Message latency ≤ 1s | 1. Send message 2. Stopwatch on both screens | Message appears on receiver screen in ≤ 1 second. | Run 10 times — all must be ≤ 1s |
| TC-M02 | FR-04.2 | Bubble alignment correct | 1. Send from A to B 2. Check both screens | A: message on right blue. B: same message on left grey. | Alignment never flips |
| TC-M03 | FR-04.5 | 200-char limit enforced | 1. Type 200 chars 2. Try to type 201st | 201st character blocked. Counter shows 200/200. | Bangla chars: 200 chars not 200 bytes |
| TC-M04 | FR-05.1 | Progress bar visible always | 1. Open chat screen 2. Look for progress bar | 4dp bar visible below header at all times. | Never hidden |
| TC-M05 | FR-05.2 | Progress bar colours correct | 1. Send messages to 13, 14, 17, 20 | Green at 13, yellow at 14, orange at 17, red at 20. | Colour changes at exact counts |
| TC-M06 | FR-05.4 | Input disabled at 20 messages | 1. Send/receive 20 total 2. Try to type | Input field greyed. Send button disabled. Cannot type. | "End Chat" button appears |
| TC-M07 | FR-04.6 | Zero messages on disk | 1. Chat for 10 messages 2. Check Room DB | Room DB has zero message records. DataStore has zero messages. | Critical security test |
| TC-M08 | EC-MSG-02 | Bangla message round-trip | 1. Send 200-char Bangla message 2. Check receiver | Exact Bangla text appears on receiver. No character corruption. | Test multiple Bangla characters |
| TC-M09 | EC-MSG-03 | Emoji message round-trip | 1. Send message with 🔥💨🎉 emoji 2. Check receiver | Exact emoji sequence preserved on receiver screen. | 4-byte Unicode test |

## 7.5 File Transfer & 10s Vanish Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-F01 | FR-06.2 | 25MB limit enforced | 1. Select 26MB file 2. Check error | Error toast shown. Transfer does not start. | Exact 25MB should be accepted |
| TC-F02 | FR-06.4 | Progress shown on both sides | 1. Send 10MB file 2. Watch both screens | Both screens show progress bar updating in real-time. | Percentage accurate |
| TC-F03 | FR-07.1 | Countdown NOT auto-started | 1. Receive file 2. Do NOT tap View for 30s | After 30s, file still shows View button. Countdown has not started. | Critical behaviour test |
| TC-F04 | FR-07.2 | View tap starts countdown | 1. Receive file 2. Tap View | Full screen opens. Countdown starts from 10. Stopwatch verify. | "10s" shows at start |
| TC-F05 | FR-07.3 | Countdown accuracy | 1. Start countdown 2. Stopwatch to 0 | Viewer closes within 10.5 seconds of View tap. | ± 0.5s acceptable |
| TC-F06 | FR-07.4 | Close and reopen viewer | 1. Open viewer at 7s 2. Close 3. Reopen | Reopen shows remaining ~4–5 seconds (not reset to 10). | "Background" countdown continues |
| TC-F07 | FR-07.5 | Save stops countdown | 1. Open viewer 2. Tap Save at 6s 3. Check storage | Countdown stops. File in BlueWhisper/Received/. Survives disconnect. | Check Room DB record created |
| TC-F08 | FR-07.6 | Vanish deletes file | 1. Open viewer 2. Let countdown reach 0 | Viewer closes with animation. File NOT in cache or storage. | "Vanished 💨" in chat card |
| TC-F09 | FR-07.7 | Unsaved file wiped on disconnect | 1. Receive file 2. Do NOT view 3. Disconnect | File not found anywhere after disconnect. | Most important privacy test |
| TC-F10 | EC-FILE-06 | Save vs vanish race condition | 1. Tap Save at exactly countdown 0 (simulate with slow tap) | File is saved. Saved state wins over vanish state. | Run 5 times at different timing |

## 7.6 Data Wipe Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-W01 | FR-08.1 | Manual disconnect wipes data | 1. Chat 10 msgs 2. Tap disconnect 3. Check ViewModel | Messages list empty. Remote profile null. Within 2s. | Critical — run 5 times |
| TC-W02 | FR-08.2 | App swipe wipes data | 1. Chat 10 msgs 2. Swipe app away 3. Reopen app | Home screen shown. No message history. | "Disconnect animation" may not show |
| TC-W03 | FR-08.2 | BT off wipes data | 1. Chat 10 msgs 2. Turn BT off 3. Check state | Wipe triggered within 2s of BT off. App on home. | BroadcastReceiver test |
| TC-W04 | FR-08.2 | Out-of-range wipes data | 1. Chat 5 msgs 2. Walk out of range 3. Check state | onDisconnected fires. Wipe occurs. Home screen shown. | Test at 35m distance |
| TC-W05 | FR-08.3 | Temp files deleted on wipe | 1. Receive file (not saved) 2. Disconnect 3. Check cache | App cache/received/ directory is empty after wipe. | Critical privacy test |
| TC-W06 | FR-08.4 | Session key zeroed on wipe | 1. Active session 2. Disconnect 3. Check EncryptionEngine | sessionKey field is null. Cannot be used for decryption. | "Memory safety" test |
| TC-W07 | FR-08.6 | Profile survives wipe | 1. Chat 2. Disconnect 3. Check profile | Nickname, avatar, language all unchanged after wipe. | Profile in DataStore not ViewModel |
| TC-W08 | FR-08.6 | Saved files survive wipe | 1. Save a file during chat 2. Disconnect 3. Check files | Saved file still in BlueWhisper/Received/. Room record intact. | Confirmed by listing directory |

## 7.7 Performance & Security Test Cases

| TC-ID | Requirement | Test Scenario | Steps to Execute | Expected Result | Edge Cases |
| --- | --- | --- | --- | --- | --- |
| TC-N01 | NFR-01.1 | Message latency ≤ 1s (×20) | 1. Send 20 messages 2. Record each latency | All 20 latency measurements ≤ 1 second. | Use device timestamps |
| TC-N02 | NFR-02.1 | Background drain ≤ 3%/hr | 1. Full charge 2. Leave scanning 1 hour 3. Check battery | Battery drop ≤ 3% in 1 hour. | Screen off during test |
| TC-N03 | NFR-03.4 | Zero internet traffic | 1. Network monitor running 2. Full session 3. Check traffic | Zero bytes sent to any external IP address. | Use Android Network Inspector |
| TC-N04 | NFR-03.5 | Zero messages on disk after session | 1. 20-message session 2. Disconnect 3. Check all storage | No message data in Room, DataStore, cache, external storage. | Use file explorer and DB inspector |
| TC-N05 | NFR-03.1 | Messages encrypted in transit | 1. BT sniffer running 2. Send message 3. Inspect packets | All BT payload bytes are ciphertext. No readable text. | Advanced — use Wireshark BT |
| TC-N06 | NFR-04.1 | Works on API 26 device | 1. Install on Android 8.0 device 2. Full flow test | All features work on minimum supported API. | Samsung Galaxy J7 or emulator |
| TC-N07 | NFR-05.4 | 100% wipe reliability | 1. Run 20 disconnect tests 2. Check data after each | All 20 tests show zero data after disconnect. | Use all 5 disconnect triggers |
| TC-N08 | NFR-06.5 | Full Bangla UI | 1. Switch to Bangla 2. Navigate all 12 screens | No text overflow, no truncation, no layout break on any screen. | Manual visual check each screen |

# 8. Definition of Done — Phase 1 Complete

Phase 1 is DONE when ALL of the following criteria are met. No exceptions.

FUNCTIONAL COMPLETENESS ✅ All 22 Functional Requirements implemented and individually verified ✅ All 18 Non-Functional Requirements measured and within target metrics ✅ All 86 test cases pass (zero failures) ✅ All 50 edge cases handled gracefully (no crash, no data leak, no freeze)

QUALITY GATES ✅ App crash rate < 0.5% across 200 test sessions ✅ Zero messages found in any storage after any disconnect trigger type ✅ Zero bytes of network traffic generated during any session ✅ All 4 file types (JPG, PDF, MP3, MP4) transfer and vanish correctly ✅ Tested on minimum 5 different Android device models including API 26 ✅ Complete Bangla UI on all 12 screens with no layout breaks ✅ Signed release APK builds successfully with ProGuard

PLAY STORE READY ✅ App size ≤ 20MB (release APK) ✅ Privacy policy written (stored offline in app — no internet needed to view) ✅ Play Store listing: screenshots (all 12 screens), description in English and Bangla ✅ App icon designed in all required sizes (48dp to 512dp) ✅ Target SDK 34 compliant with all Android 14 behaviour changes

FINAL TIME ESTIMATE SUMMARY Implementation (127 dev tasks): 128 hours Testing (14 test tasks, 86 cases): 20 hours Total working hours: 148 hours At 6h/day (focused developer): 25 working days ≈ 5 weeks At 4h/day (side project pace): 37 working days ≈ 8 weeks With 20% buffer for bugs/fixes: ~178 hours total RECOMMENDED TIMELINE: 8 WEEKS FROM START TO PLAY STORE